LAS VEGAS FIRE DANCERS

MARKETING & LAUNCH PLAN

March 2026  —  Launch Strategy

Funded by Fund the Flow Arts  |  Sponsored by Pyrotechnique

# 1. Executive Summary

Las Vegas Fire Dancers (LVFD) is launching as the premier weekly fire flow jam in the Las Vegas metropolitan area. Supported by a grant from Fund the Flow Arts and sponsored by Pyrotechnique, LVFD aims to establish a safe, consistent, and welcoming space for fire performers and flow artists of all levels.

This marketing plan covers our pre-launch phase through the first six months of operation, with strategies for digital presence, community building, social media growth, and event promotion. Our primary goal is to build a core community of 50+ regular attendees within the first quarter, growing to 100+ by month six.

# 2. Goals & Key Performance Indicators

## Primary Goals

- Launch website and all social media channels before first event

- Achieve 25+ attendees at the inaugural jam

- Build a core community of 50+ regular weekly attendees within 3 months

- Grow social media following to 1,000+ across all platforms within 6 months

- Establish LVFD as the recognized weekly fire jam in the Las Vegas area

## KPI Tracking

| Metric | Month 1 Target | Month 3 Target | Month 6 Target |
| --- | --- | --- | --- |
| Weekly Attendance | 15–25 | 40–60 | 80–120 |
| Instagram Followers | 200 | 500 | 1,200 |
| Facebook Group Members | 100 | 300 | 600 |
| Website Monthly Visitors | 500 | 1,500 | 3,000 |
| Email List Subscribers | 50 | 200 | 500 |
| YouTube Subscribers | 50 | 150 | 400 |

# 3. Launch Timeline

## Phase 1: Pre-Launch (Weeks 1–4)

Objective: Build anticipation, establish digital presence, connect with existing flow arts community.

| Week | Action Items | Owner |
| --- | --- | --- |
| Week 1 | Finalize branding. Deploy website to GitHub Pages. Create all social media accounts. Set up email list (Mailchimp). | Marketing Lead |
| Week 2 | Begin daily social media posting. Announce LVFD on Reddit r/flowarts, Facebook flow groups. Reach out to local flow artists and fire performers. | Social Media / Outreach |
| Week 3 | Launch countdown content series. Post safety commitment video. Partner outreach to local fire/flow shops, venues. | Content / Partnerships |
| Week 4 | Final event details announcement. Location reveal. Equipment/safety checklist post. Email blast to subscribers. | All Hands |

## Phase 2: Launch & First Month (Weeks 5–8)

Objective: Execute a successful first jam, capture high-quality content, iterate based on feedback.

- Host inaugural jam with designated photographer/videographer

- Post event recap within 24 hours across all channels

- Collect attendee feedback via short survey (Google Forms)

- Start weekly content cadence: Monday teaser, Wednesday safety tip, Friday event reminder, Sunday recap

- Feature community members in “Spinner Spotlight” series

## Phase 3: Growth (Months 2–6)

Objective: Scale community, add programming, establish partnerships.

- Introduce monthly themed jams (e.g., “New Spinners Night,” “Big Burn,” “Glow Flow”)

- Launch workshop series: safety certification, beginner poi, staff technique

- Cross-promote with Vegas entertainment and arts communities

- YouTube tutorial series launch

- Pursue local media coverage (Vegas Seven, Las Vegas Weekly, local TV)

# 4. Digital Marketing Strategy

## Website (GitHub Pages)

The LVFD website serves as the central hub for all event information, safety resources, and community connection. Hosted on GitHub Pages for zero hosting cost and easy deployment.

### Key Features

- Animated hero with fire particle effects and next-event countdown

- About section with mission, community values, and sponsor information

- Weekly schedule with location, time, and what-to-bring info

- Safety section with protocols, equipment guidelines, and code of conduct

- Community gallery showcasing performances and events

- Email signup form for weekly updates

- Mobile-responsive dark theme consistent with brand guidelines

### SEO Strategy

- Primary Keywords: fire dancing las vegas, fire flow jam vegas, fire spinning las vegas, fire poi las vegas

- Secondary Keywords: flow arts community, fire performance lessons, fire dancing meetup

- Ensure proper meta tags, Open Graph tags for social sharing, and structured data markup

## Social Media Content Calendar

Consistent posting schedule across all platforms with tailored content for each.

| Day | Instagram | Facebook | TikTok |
| --- | --- | --- | --- |
| Monday | Teaser/countdown to jam | Event page update | Quick tip video |
| Tuesday | Safety Tip Tuesday | Safety article share | — |
| Wednesday | Technique tutorial Reel | Community discussion post | Tutorial clip |
| Thursday | Spinner Spotlight | Member feature story | — |
| Friday | Event reminder + details | Event reminder w/ RSVP | Hype video |
| Saturday | Live stories from jam | Live stream / check-in | Live behind-scenes |
| Sunday | Photo/video recap | Full recap + gallery | Best moments edit |

## Email Marketing

- Platform: Mailchimp (free tier for first 500 subscribers)

- Weekly Newsletter: Sent every Thursday — jam details, safety tip of the week, community highlight, sponsor shoutout

- Welcome Sequence: 3-email automated series for new subscribers — welcome + what to expect, safety basics, community introduction

- Special Blasts: Themed events, workshop announcements, major milestones

# 5. Community Building Strategy

## Grassroots Outreach

- Connect with existing LV flow arts practitioners through Facebook groups, Reddit, and word of mouth

- Partner with local yoga studios, martial arts gyms, and dance studios for cross-promotion

- Attend and table at local arts events, First Friday, and maker fairs

- Distribute branded stickers and flyers at flow-friendly retail locations

- Host a free “Intro to Flow Arts” workshop as a launch event to attract newcomers

## Partnerships

- Pyrotechnique: Co-branded content, equipment demos, sponsored giveaways at jams

- Local Fire Prop Shops: Cross-promotion, discount codes for LVFD community members

- Flow Arts Festivals: Promote regional events (Flow Fest, Kinetic Fire, etc.) in exchange for LVFD mentions

- Local Media: Pitch human-interest stories to Vegas media outlets about the community and safety-first approach

## Retention & Engagement

- Monthly themed jams to keep content fresh and provide variety

- Skill-level badges/wristbands (Beginner, Intermediate, Advanced, Safety Crew)

- Quarterly community socials (non-fire gatherings for bonding)

- Annual “Anniversary Burn” celebration event

# 6. Budget Overview

As a grant-funded project, cost efficiency is paramount. Many marketing activities leverage free or low-cost tools.

| Item | Monthly Cost | Notes |
| --- | --- | --- |
| Website Hosting | $0 | GitHub Pages (free) |
| Domain Name | $1/mo | Annual registration |
| Mailchimp | $0 | Free tier up to 500 subs |
| Canva Pro | $13/mo | Social media graphics |
| Social Media Ads | $50–100/mo | Targeted local reach |
| Printed Materials | $25–50/mo | Flyers, stickers, cards |
| Photography/Video | $0–50/mo | Community volunteers + occasional pro |
| Safety Equipment | Grant funded | Fire blankets, extinguishers, first aid |
| TOTAL | $89–214/mo | Highly scalable based on needs |

# 7. Measurement & Reporting

- Weekly: Attendance count, social media engagement rates, new followers

- Monthly: Full analytics report (web traffic, social growth, email open rates, attendance trends)

- Quarterly: Community survey, sponsor report, strategic review and plan adjustments

- Tools: Google Analytics (website), Meta Business Suite (IG/FB), TikTok Analytics, Mailchimp Reports

This marketing plan is designed to be executed iteratively. Review and adjust tactics monthly based on data and community feedback. The fire burns brighter when we all contribute.